## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | (Fill your Project Number here)
PROJECT NAME | (Fill your project name here)
PROJECT MENTOR (sponsor) | (Put your Project Mentor (sponsor) name here)
TEAM MEMBERS | Team Mamber Name 1
Team Member Name 2
Team Member Name 3
Team Member Name 4
Team Member Name 5

## Status
PROJECT NUMBER | Team 12
PROJECT NAME | ICanCare
PROJECT MENTOR (sponsor) | Dr. Pawan Gupta
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Internal meetings | Coordination | Navya, Rohitha | 1.5 | 2 | Done | every teammate invested the same time | -0.5 | 25
Client Meetings | Coordination | Manas Agarwal | 1 | 1 | Done | every teammate invested the same time | 0 | 0
Design Blue-print of the website | Documentation | Krrish, Yogeswari | 2 | 2 | Ongoing |  | 0 | 0
Research in that domain | Preparation | Navya, | 2 | 3 | Done | Subject to further changes | -1 | 33.3333
Research existing technology/apps | Preparation | Rohitha | 1.5 | 2 | Ongoing |  | -0.5 | 25
Project requirements feasability | Preparation | Krrish, Manas | 1 | 2 | Done |  | -1 | 50
MoMs updation | Documentation | Krrish, Manas | 1 | 2 | Done |  | -1 | 50
Status tracker | Documentation | Yogeswari | 0.5 | 0.5 | Done |  | 0 | 0
Week 2 (January 22 - January 28)
Internal meetings | Coordination | Rohitha | 1 | 2 | Done | every teammate invested the same time | -1 | 50
Client Meetings | Coordination | Manas | 1 | 1.5 | Done | every teammate invested the same time | -0.5 | 33.3333
Status Tracker | Documentation | Navya | 0.5 | 0.5 | Done |  | 0 | 0
MoMs updation | Documentation | Yogeswari | 1 | 1 | Done |  | 0 | 0
Learn Node | Preparation | Manas, Krrish | 2 | 3 | Ongoing |  | -1 | 33.3333
Project Synopsis | Preparation | Navya, Yogeswari | 2 | 3 | Done |  | -1 | 33.3333
Research existing technology/apps | Preparation | Rohitha | 1 | 1 | Done |  | 0 | 0
Design Blue-print of the website | Documentation | Yogeswari | 1 | 2 | Ongoing |  | -1 | 50
Week 3 (January 29 - February 4)
Internal meetings | Coordination | Navya | 0.5 | 0.5 | Done |  | 0 | 0
Learn Node | Preparation | Manas, Krrish | 2 | 3 | Done
Learn React | Preparation | Rohitha, Yogeswari | 3 | 4 | Done
Design Blue-print of the website | Documentation | Yogeswari | 1.5 | 1.5 | Done |  | 0 | 0
Week 4 (February 5 - February 11)
Client Meetings | Coordination | Manas, Krrish | 1 | 1 | Done |  | 0 | 0
Internal meetings | Coordination | Navya | 1.5 | 2 | Done
Basic Authentication for Patients and Doctor (Frontend+Backend) | Development | Yogeswari, Rohitha | 5 | 6 | Done
Status Tracker | Documentation | Rohitha, Yogeswari | 0.5 | 0.5 | Done
Week 5 (February 12 - February 18)
Client Meetings | Coordination | Manas, Yogeswari | 3 | 3 | Done |  | 0 | 0
MoMs updation | Documentation | Krrish | 2 | 2 | Done
Internal Meetings | Coordination | Navya, Rohitha | 3 | 3.5 | Done
Doctor and new cases page (Frontend and backend) and swagger | Development | Manas, Krrish | 15 | 15 | Done |  | 0 | 0
SRS document | Documentation | Rohitha, Yogeswari | 6 | 6 | Done
Status Tracker | Documentation | Navya | 1 | 1 | Done |  | 0 | 0
Week 6 (February 19 - February 25)
Client Meetings | Coordination | Rohitha, Yogeswari | 3 | 3 | Done |  | 0 | 0
Internal Meetings | Coordination | Rohitha, Yogeswari | 3 | 2 | Done |  | 1 | 50
Research and learning for the functionality | Preparation | Navya, Krrish | 6 | 6.5 | Done |  | -0.5 | 7.6923
MoMs updation | Documentation | Manas | 2 | 2 | Done |  | 0 | 0
Chat and upload functionality(Frontend and Backend) | Development | Krrish, Manas | 17 | 17 | Done |  | 0 | 0
Status Tracker | Documentation | Navya | 1 | 0.5 | Done |  | 0.5 | 100
Week 7 (February 26 - March 4)
Client Meetings | Coordination | Manas | 3 | 3 | Done |  | 0 | 0
Internal Meetings | Coordination | Rohitha, Yogeswari | 3 | 3 | Done |  | 0 | 0
MoMs updation | Documentation | Krrish | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Navya | 1 | 1 | Done |  | 0 | 0
Week 8 (March 5 - March 11)
Client Meetings | Coordination | Manas | 1 | 0.5 | Done |  | 0.5 | 100
Internal Meetings | Coordination | Manas, Krrish | 2 | 2 | Done |  | 0 | 0
MoMs updation | Documentation | Krrish | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Navya | 1 | 1 | Done |  | 0 | 0
Admin fuctionalities | Development | Rohitha, Yogeswari | 15 | 17 | Done |  | -2 | 11.7647
Learning of HIPPA regulations | Preparation | Rohitha, Yogeswari | 4 | 4 | Done |  | 0 | 0
Design document | Documentation | Navya | 5 | 5 | Done |  | 0 | 0
Week 9 (March 12 - March 18)
Client Meetings | Coordination | Manas | 3 | 3 | Done |  | 0 | 0
Internal Meetings | Coordination | Rohitha | 3 | 6 | Done |  | -3 | 50
MoMs updation | Documentation | Krrish | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Navya | 1 | 1 | Done |  | 0 | 0
Updating schedule meeting functionality | Development | Yogeswari, Manas | 15 | 17 | Done |  | -2 | 11.7647
Updating User Interface | Interfaces | Krrish | 8 | 8 | Done |  | 0 | 0
PPT and demo (R1) | Preparation | Rohitha, Yogeswari | 5 | 5 | Done |  | 0 | 0
Testing (R1) | Testing | Navya | 6 | 4 | Done |  | 2 | 50
Presentation (R1) | Delivery | Rohitha, Yogeswari, Manas, Krrish, Navya | 0.5 | 0.5 | Planned |  | 0 | 0
Week 10 (March 19 - March 25)
Client Meetings | Coordination | Manas | 3 | 3 | Done |  | 0 | 0
Internal Meetings | Coordination | Yogeswari, Rohitha | 3 | 6 | Done |  | -3 | 50
MoMs updation | Documentation | Krrish | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Navya | 1 | 1 | Done |  | 0 | 0
Presentation (R1) | Delivery | Rohitha, Yogeswari, Manas, Krrish, Navya | 0.5 | 0.5 | Done |  | 0 | 0
Document updates | Documentation | Rohitha, Navya | 6 | 6 | Done |  | 0 | 0
Code updates | Development | Krrish, Manas, Yogeswari | 15 | 15 | Done |  | 0 | 0
Week 11 (March 26 - March 31)
Client Meetings | Coordination | Manas | 3 | 3 | Done |  | 0 | 0
Internal Meetings | Coordination | Yogeswari, Rohitha | 3 | 6 | Done |  | -3 | 50
MoMs updation | Documentation | Krrish | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Navya | 1 | 1 | Done |  | 0 | 0
Evaluation (R1) | Delivery | Yogeswari, manas, krrish, navya, Rohitha | 0.5 | 1 | Done |  | -0.5 | 50
Code updates | Development | Yogeswari, Rohitha | 6 | 6 | Done |  | 0 | 0
PDF text extraction | Testing | Manas, Krrish | 10 | 15 | Done |  | -5 | 33.3333
Document updates | Documentation | Navya | 2 | 3 | Done |  | -1 | 33.3333
Week 12 (April 1 - April 6)
Client Meetings | Coordination | Manas, Krrish | 3 | 3 | Done |  | 0 | 0
Internal Meetings | Coordination | Yogeswari, Rohitha | 3 | 6 | Done |  | -3 | 50
MoMs updation | Documentation | Navya | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Navya | 1 | 1 | Done |  | 0 | 0
AI Feature Integration | Preparation | Manas, Krrish | 11 | 12 | Done |  | -1 | 8.3333
Code updates (Additional features) | Development | Yogeswari, Rohitha | 9 | 9 | Done |  | 0 | 0
Week 13 (April 7 - April 12)
Client Meetings | Coordination | Manas | 3 | 3 | Done |  | 0 | 0
Internal Meetings | Coordination | Yogeswari, Rohitha | 3 | 6 | Done |  | -3 | 50
MoMs updation | Documentation | Krrish | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Navya | 1 | 1 | Done |  | 0 | 0
AI summary feature | Preparation | Manas, Krrish | 11 | 12 | Done |  | -1 | 8.3333
Code updates (Additional features) | Development | Rohitha | 12 | 12 | Done |  | 0 | 0
Test plan tracker | Documentation | Yogeswari | 5 | 5 | Done |  | 0 | 0
Deployment (learning+implementation) | Preparation | Navya | 10 | 10 | Done |  | 0 | 0
Week 14 (April 13 - April 20)
Client Meetings | Coordination | Manas | 3 | 3 | Done |  | 0 | 0
Internal Meetings | Coordination | Yogeswari, Rohitha | 3 | 6 | Done |  | -3 | 50
MoMs updation | Documentation | Krrish | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Navya | 1 | 1 | Done |  | 0 | 0
Code updates (Debugging) | Development | Krrish | 6 | 6 | Done |  | -1 | 8.3333
AI summary feature | Development | Manas | 11 | 12 | Done |  | 0 | 0
Code updates (Additional features) | Development | Rohitha | 9 | 9 | Done |  | 0 | 0
Document updates | Documentation | Yogeswari | 5 | 5 | Done |  | 0 | 0
Deployment | Delivery | Navya | 10 | 10 | Done |  | #REF! | #REF!
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically